## COVER
UNICEM PRMS UPGRADE PROJECT
FEED & DED
MASTER DELIVERABLES REGISTER (MDR)
2506600-IESL-MDR-A-0001
1 | 2025-10-06 | Issued for Use | C.O | T.B | O.A
0 | 2025-08-08 | Issued for Use | D.E | T.B | O.A
B | 2025-07-01 | Issued for Review | A.J | O.B | I.S
REV | DATE | DESCRIPTION | ORIG | CHK | APPR

## MDR
Technical safety abbreviation
[8 empty] | IFR | [10 empty] | IFD | [11 empty] | IFH | [5 empty] | AFC | [7 empty] | REMARKS
CONTRATOR's Doc No |  | S/No | DOC Number | DOC Title |  |  | START | Rev B | [6 empty] | TR NO | Date Sent | Rev Sta | Issue For | Rev 0 |  |  |  | TR No | Date Sent | Rev Sta | Issue For | Next Rev | [9 empty] | Rev 1 |  | TR No
[5 empty] | Status | Definition |  | Planned | Actual | Transmittal | Rev | Transmittal Received | Date | Code |  |  |  |  | Planned | Actual | Transmittal | Rev | [5 empty] | Transmittal Received | Date | Code | Actual | Transmittal | Rev | Transmittal Received | Date | Code | Planned | Actual |  | Transmittal | Rev | Transmittal Received | Date | Code
Project Management & Administration
|  | 1 | 2506600-IESL-BOD-A-0001 | Project Basis of design | IFU |  |  | 2025-07-18 | 2025-08-14 | PRMS-IESL-AGAS-TRN-0068 | B | 2506600-AGAS-IESL-TRM-0043 | 2025-09-04 | C2 |  |  |  |  | 2025-08-02 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0231 | 0 | [14 empty] | 2025-08-12
|  | 2 | 2506600-IESL-SHD-A-0001 | Project Schedule | RE-IFU |  |  | 2025-07-01 | 2025-07-04 | PRMS-IESL-AGAS-TRN-0002 | B | 2506600-AGAS-IESL-TRM-0008 | 2025-07-09 | C2 |  |  |  |  | 2025-07-16 | 2025-07-16 | PRMS-IESL-AGAS-TRN-0011 / 0039 | 0-B | [5 empty] | 2506600-AGAS-IESL-TRM-0017 / 0023 | 2025-08-06 | C2 | [6 empty] | 2025-07-26
|  | 3 | 2506600-IESL-PEP-A-0001 | Project Execution Plan | AFC |  |  | 2025-07-02 | 2025-07-04 | PRMS-IESL-AGAS-TRN-0003 | B | 2506600-AGAS-IESL-TRM-0011 | 2025-07-10 | C2 |  |  |  |  | 2025-07-17 | 2025-07-17 | PRMS-IESL-AGAS-TRN-0015 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 | [6 empty] | 2025-07-27 | 2025-08-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0089 | 1 | 2506600-AGAS-IESL-TRM-0076 | 2025-09-25 | C1
|  | 4 | 2506600-IESL-PLN-Q-0001 | Project Quality Plan | IFU |  |  | 2025-07-02 | 2025-07-22 | PRMS-IESL-AGAS-TRN-0023 | B | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 |  |  |  |  | 2025-07-17 | 2025-07-31 | PRMS-IESL-AGAS-TRN-0041 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C1 | [6 empty] | 2025-07-27
|  | 5 | 2506600-IESL-SOW-K-0001 | Construction Scope of Work | IFR |  |  | 2025-09-01 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0216 | B | [7 empty] | 2025-09-16 | [17 empty] | 2025-10-06
|  | 6 | 2506600-IESL-PLN-S-0001 | HSE Plan | IFD |  |  | 2025-07-02 | 2025-07-04 | PRMS-IESL-AGAS-TRN-0004 | B | 2506600-AGAS-IESL-TRM-0012 | 2025-07-10 | C2 |  |  |  |  | 2025-07-17 | 2025-08-29 | PRMS-IESL-AGAS-TRN-0111 | 0 | [14 empty] | 2025-07-27
|  | 7 | 2506600-IESL-MDR-A-0001 | Master Deliverables Register and Progress Measurement System | RE-IFU |  |  | 2025-07-02 | 2025-07-01 | PRMS-IESL-AGAS-TRN-0001 | B | 2506600-AGAS-IESL-TRM-0019 | 2025-07-23 | C2 |  |  |  |  | 2025-07-17 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0058 / 0244 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0043 | 2025-09-04 | C2 | [6 empty] | 2025-07-27
|  | 8 | 2506600-IESL-PRD-A-0001 | Project Control Procedure | IFU |  |  | 2025-07-06 | 2025-07-04 | PRMS-IESL-AGAS-TRN-0005 | B | 2506600-AGAS-IESL-TRM-0011 | 2025-07-10 | C2 |  |  |  |  | 2025-07-21 | 2025-07-11 | PRMS-IESL-AGAS-TRN-0008 | 0 | 2506600-AGAS-IESL-TRM-0011 |  |  |  |  | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C1 | [6 empty] | 2025-07-31
|  | 9 | 2506600-IESL-PLN-A-0001 | Document Control Plan | IFU |  |  | 2025-07-11 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0066 | B | 2506600-AGAS-IESL-TRM-0043 | 2025-09-04 | C2 |  |  |  |  | 2025-07-26 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0196 | 0 | [14 empty] | 2025-08-05
|  | 10 | WORKSHOP | HAZID Workshop |  |  |  | 2025-08-18 | 2025-08-18 | [9 empty] | NA | [17 empty] | NA | [7 empty] | Subject to CPY approval
|  | 11 | WORKSHOP | HAZOP Workshop |  |  |  | 2025-09-18 | 2025-09-19
|  | 10 | 2506600-IESL-RPT-S-0001 | HAZOP/HAZID Review Report |  |  |  | 2025-09-08 | [10 empty] | 2025-09-23 | [17 empty] | 2025-10-03
DESIGN REVIEW | Technical Design Review | 12 | DESIGN REVIEW | Technical Design Review |  |  |  | 2025-09-30 | [10 empty] | NA | [17 empty] | NA | [7 empty] | Subject to CPY approval
|  | 13 | 2506600-IESL-RPT-A-0001 | Design Review Report |  |  |  | 2025-10-10 | [10 empty] | 2025-09-27 | [17 empty] | 2025-10-07
|  | 14 | 2506600-IESL-EST-A-0001 | Cost Estimation Report |  |  |  | 2025-09-07 | [10 empty] | 2025-09-22 | [17 empty] | 2025-10-02
|  | 15 | 2506600-IESL-RPT-A-0002 | Site Visit Report | AFC |  |  | 2025-07-15 | 2025-07-16 | PRMS-IESL-AGAS-TRN-0012 | B | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 |  |  |  |  | 2025-07-30 | 2025-08-07 | PRMS-IESL-AGAS-TRN-0054 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0038 | 2025-09-01 | C2 | [6 empty] | 2025-08-09 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0163 | 1 | 2506600-AGAS-IESL-TRM-0076 | 2025-09-25 | C1
|  | 16 | 2506600-IESL-RPT-A-0003 | Project Close-Out Report | [32 empty] | 2025-10-28
Technical Safety
|  | 1 | 2506600-IESL-TOR-S-0001 | HAZOP Terms of Reference | AFC |  |  | 2025-07-15 | 2025-07-23 | PRMS-IESL-AGAS-TRN-0025 | B | 2506600-AGAS-IESL-TRM-0020 | 2025-07-28 | C2 |  |  |  |  | 2025-08-04 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0056 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0029 | 2025-08-20 | C1 | [6 empty] | 2025-08-24 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0149 / 0186 | 1 / 2 | 2506600-AGAS-IESL-TRM-0062 / 0083 | 2025-09-18 | C2 / C1
|  | 2 | 2506600-IESL-RPT-S-0002 | HAZOP Close Out Report |  |  |  | 2025-10-02 | [10 empty] | 2025-10-09 | [17 empty] | 2025-10-19
|  | 3 | 2506600-IESL-TOR-S-0002 | HAZID Terms Of Reference | AFC |  |  | 2025-07-06 | 2025-07-23 | PRMS-IESL-AGAS-TRN-0027 | B | 2506600-AGAS-IESL-TRM-0020 | 2025-07-28 | C2 |  |  |  |  | 2025-07-26 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0056 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0029 | 2025-08-20 | C1 | [6 empty] | 2025-08-15 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0133 | 1 | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C2
|  | 4 | 2506600-IESL-RPT-S-0003 | HAZID Close Out Report | IFR |  |  | 2025-09-03 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0161 | B | 2506600-AGAS-IESL-TRM-0069 | 2025-09-23 | C2 |  |  |  |  | 2025-09-18 | [17 empty] | 2025-10-08
|  | 5 | 2506600-IESL-STD-S-0001 | HAZOP Study Report | IFR |  |  | 2025-09-24 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0217 | B | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1 |  |  |  |  | 2025-10-03 | [17 empty] | 2025-10-13
|  | 6 | 2506600-IESL-STD-S-0002 | HAZID Study Report | AFC |  |  | 2025-08-29 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0107 | B | 2506600-AGAS-IESL-TRM-0048 | 2025-09-08 | C2 |  |  |  |  | 2025-09-08 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0152 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C1 | [6 empty] | 2025-09-28 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0201 | 1 | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1
|  | 7 | 2506600-IESL-PHS-S-0001 | HSE Design Philosophy | AFC |  |  | 2025-07-02 | 2025-08-29 | PRMS-IESL-AGAS-TRN-0094 | B | 2506600-AGAS-IESL-TRM-0038 / 0045 | 2025-09-01 | C2 |  |  |  |  | 2025-07-22 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0150 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C1 | [6 empty] | 2025-08-11 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0201 | 1 | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1
|  | 8 | 2506600-IESL-SHD-S-0001 | Hazardous Area Classification Schedule | IFD |  |  | 2025-07-30 | 2025-08-29 | PRMS-IESL-AGAS-TRN-0113 | B | 2506600-AGAS-IESL-TRM-0048 | 2025-09-08 | C2 |  |  |  |  | 2025-08-19 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0228 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1 | [6 empty] | 2025-09-08
|  | 9 | 2506600-IESL-DRA-S-0001 | Hazardous Area Classification drawings | IFD |  |  | 2025-08-28 | 2025-09-02 | PRMS-IESL-AGAS-TRN-0118 | B | 2506600-AGAS-IESL-TRM-0048 | 2025-09-08 | C2 |  |  |  |  | 2025-09-17 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0223 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2 | [6 empty] | 2025-10-07
|  | 10 | 2506600-IESL-LYT-S-0001 | Firefighting and Safety Equipment Layout | AFC |  |  | 2025-08-29 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0108 | B | 2506600-AGAS-IESL-TRM-0045 | 2025-09-04 | C2 |  |  |  |  | 2025-09-18 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0151 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C1 | [6 empty] | 2025-10-08 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0201 | 1
|  | 11 | 2506600-IESL-LYT-S-0002 | Escape & Evacuation Layout Drawing | AFC |  |  | 2025-08-28 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0108 | B | 2506600-AGAS-IESL-TRM-0045 | 2025-09-04 | C2 |  |  |  |  | 2025-09-17 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0151 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C1 | [6 empty] | 2025-10-07 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0201 | 1
|  | 12 | 2506600-IESL-LYT-S-0003 | Safety Signage Layout Drawing | AFC |  |  | 2025-08-29 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0100 | B | 2506600-AGAS-IESL-TRM-0045 | 2025-09-04 | C2 |  |  |  |  | 2025-09-18 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0151 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0062 | 2025-09-18 | C1 | [6 empty] | 2025-10-08 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0201 | 1
Process
|  | 1 | 2506600-IESL-RPT-P-0001 | Flow Assurance - Slugging Transient Analysis and Report | AFC |  |  | 2025-08-01 | 2025-08-06 | PRMS-IESL-AGAS-TRN-0051 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-08-22 | 2025-09-01 | PRMS-IESL-AGAS-TRN-0116 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C1 | [6 empty] | 2025-09-12 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0220 | 1
|  | 2 | 2506600-IESL-RPT-P-0002 | HYSYS Simulation & Report | AFC |  |  | 2025-07-18 | 2025-07-29 | PRMS-IESL-AGAS-TRN-0033 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-08-15 | 2025-08-20 | PRMS-IESL-AGAS-TRN-0083 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C1 | [6 empty] | 2025-09-12 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0144 | 1
|  | 3 | 2506600-IESL-RPT-P-0003 | Heat & Material Balance Report | IFD |  |  | 2025-07-18 | 2025-08-01 | PRMS-IESL-AGAS-TRN-0042 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-08-15 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0105 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C2 | [6 empty] | 2025-09-12
|  | 4 | 2506600-IESL-NTS-P-0001 | Line Sizing Calculation Note | AFC |  |  | 2025-08-01 | 2025-08-19 | PRMS-IESL-AGAS-TRN-0077 | B | 2506600-AGAS-IESL-TRM-0040 | 2025-09-02 | C2 |  |  |  |  | 2025-08-22 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0147 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C1 | [6 empty] | 2025-09-19 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0218 | 1
|  | 5 | 2506600-IESL-RPT-P-0004 | Equipment Sizing & Selection Report | IFD |  |  | 2025-08-08 | 2025-09-02 | PRMS-IESL-AGAS-TRN-0119 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C2 |  |  |  |  | 2025-08-29 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0169 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0076 | 2025-09-25 | C2 | [6 empty] | 2025-09-19
|  | 6 | 2506600-IESL-RPT-P-0005 | Utility Balance Report | AFC |  |  | 2025-07-25 | 2025-08-06 | PRMS-IESL-AGAS-TRN-0052 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-08-15 | 2025-08-21 | PRMS-IESL-AGAS-TRN-0085 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 | [6 empty] | 2025-09-19 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0155 | 1
|  | 7 | 2506600-IESL-LST-P-0001 | Line List | IFD |  |  | 2025-08-08 | 2025-09-01 | PRMS-IESL-AGAS-TRN-0115 | B | 2506600-AGAS-IESL-TRM-0048 | 2025-09-08 | C2 |  |  |  |  | 2025-08-29 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0190 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C2 | [6 empty] | 2025-09-26
|  | 8 | 2506600-IESL-RPT-P-0006 | GHG Emission Report | IFR |  |  | 2025-08-29 | 2025-09-22 | PRMS-IESL-AGAS-TRN-0199 | B | 2506600-AGAS-IESL-TRM-0082 | 2025-10-02 | C2 | [22 empty] | 2000-01-14
|  | 9 | 2506600-IESL-PHS-P-0001 | Process Operating and Control Philosophy -Update | AFC |  |  | 2025-08-01 | 2025-08-29 | PRMS-IESL-AGAS-TRN-0109 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C2 |  |  |  |  | 2025-08-22 | 2025-09-15 | PRMS-IESL-AGAS-TRN-0171 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C1 | [6 empty] | 2025-09-26 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0220 | 1
|  | 10 | 2506600-IESL-PHS-P-0002 | Isolation Philosophy - Update | AFC |  |  | 2025-07-25 | 2025-07-23 | PRMS-IESL-AGAS-TRN-0024 | B | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 |  |  |  |  | 2025-08-15 | 2025-08-18 | PRMS-IESL-AGAS-TRN-0076 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 | [6 empty] | 2025-09-19 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0140 | 1
|  | 11 | 2506600-IESL-NTS-P-0002 | Control Valve Sizing Calculation Note | AFC |  |  | 2025-07-25 | 2025-07-25 | PRMS-IESL-AGAS-TRN-0025 | B | 2506600-AGAS-IESL-TRM-0022 | 2025-07-31 | C2 |  |  |  |  | 2025-08-15 | 2025-08-18 | PRMS-IESL-AGAS-TRN-0075 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 | [6 empty] | 2025-09-15 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0148 | 1
|  | 12 | 2506600-IESL-DTS-P-0001 | INLET GAS SCRUBBER PROCESS DATASHEET | AFC |  |  | 2025-08-15 | 2025-09-03 | PRMS-IESL-AGAS-TRN-0121 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C1 |  |  |  |  | 2025-09-05 | 2025-09-15 | PRMS-IESL-AGAS-TRN-0172 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C1 | [6 empty] | 2025-10-10 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0214 | 1
|  | 13 | 2506600-IESL-DTS-P-0002 | PROCESS DATASHEET - PRESSURE SAFETY VALVES | IFR |  |  | 2025-08-15 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0130 | B | 2506600-AGAS-IESL-TRM-0059 | 2025-09-17 | C2 |  |  |  |  | 2025-09-05 | [17 empty] | 2025-10-10
|  | 14 | 2506600-IESL-DTS-P-0003 | Process Datasheet - Control Valve | AFC |  |  | 2025-08-15 | 2025-07-30 | PRMS-IESL-AGAS-TRN-0037 | B | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 |  |  |  |  | 2025-09-05 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0157 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C2 | [6 empty] | 2025-10-10 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0214 | 1
|  | 15 | 2506600-IESL-DTS-P-0004 | PROCESS DATASHEET - RESTRICTION ORIFICE | IFD |  |  | 2025-08-15 | 2025-09-15 | PRMS-IESL-AGAS-TRN-0173 | B | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C2 |  |  |  |  | 2025-09-05 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0215 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1 | [6 empty] | 2025-10-10
|  | 16 | 2506600-IESL-DTS-P-0005 | PROCESS DATASHEET - SALES GAS HEATER | AFC |  |  |  | 2025-09-10 | PRMS-IESL-AGAS-TRN-0154 | B | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C1 | [23 empty] | 2025-10-03 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0238 | 0
|  | 17 | 2506600-IESL-RPT-P-0007 | PSV Calculation Summary Report | IFD |  |  | 2025-08-11 | 2025-09-03 | PRMS-IESL-AGAS-TRN-0124 | B | 2506600-AGAS-IESL-TRM-0059 | 2025-09-17 | C2 |  |  |  |  | 2025-09-01 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0192 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2 | [6 empty] | 2025-09-22
|  | 18 | 2506600-IESL-RPT-P-0010 | Dynamic Blowdown Study Report | IFD |  |  |  | 2025-08-29 | PRMS-IESL-AGAS-TRN-00112 | B | 2506600-AGAS-IESL-TRM-0055 | 2025-09-14 | C2 | [5 empty] | 2025-09-23 | PRMS-IESL-AGAS-TRN-0205 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1
|  | 19 | 2506600-IESL-RPT-P-0011 | Vent Radiation and Noise Report | IFR |  |  |  | 2025-09-30 | PRMS-IESL-AGAS-TRN-0222 | B
|  | 20 | 2506600-IESL-RPT-P-0012 | Vent Dispersion Analysis Report | IFD |  |  |  | 2025-09-10 | PRMS-IESL-AGAS-TRN-00156 | B | 2506600-AGAS-IESL-TRM-0059 | 2025-09-17 | C2 | [5 empty] | 2025-09-19 | PRMS-IESL-AGAS-TRN-0195 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2
|  | 21 | 2506600-IESL-RPT-P-0013 | Vent Network Hydraulic Study Report | IFR |  |  |  | 2025-09-22 | PRMS-IESL-AGAS-TRN-0202 | B | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2
|  | 22 | 202-1-PFD-001 | Process Flow Diagram (1 Nos) - Existing | IFD |  |  | 2025-07-18 | 2025-07-21 | PRMS-IESL-AGAS-TRN-0018 | B | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 |  |  |  |  | 2025-08-15 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0106 | 51 | [5 empty] | 2506600-AGAS-IESL-TRM-0046 | 2025-09-08 | C2 | [6 empty] | 2025-09-19
|  | 23 | 202-1-PID-001 | P&ID - Legend & Symbols | IFH |  |  |  | 2025-08-05 | PRMS-IESL-AGAS-TRN-0048 | 0-B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 | [5 empty] | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 1 | [5 empty] | 2506600-AGAS-IESL-TRM-0036 / 0041 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 2
|  | 24 | 202-1-PID-009 | P&ID - Scrapper Launcher at City Gate and Unicem PRMS | IFH |  |  | 2025-08-01 | 2025-08-05 | PRMS-IESL-AGAS-TRN-0048 | 51-B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 |  |  |  |  | 2025-08-22 | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 52 | [5 empty] | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 53 |  |  |  | 2025-09-26
|  | 25 | 202-1-PID-010 | P&ID - Metering Skid at UNICEM PRMS | IFH |  |  |  | 2025-08-06 | PRMS-IESL-AGAS-TRN-0051 | B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 | [5 empty] | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 51 | [5 empty] | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 52
|  | 26 | 202-1-PID-011 | P&ID - Slop Tank, Vent Scrubber and Vent Stack at Unicem PRMS | IFH |  |  |  | 2025-08-04 | PRMS-IESL-AGAS-TRN-0046 | 50-B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 | [5 empty] | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 51 | [5 empty] | 2506600-AGAS-IESL-TRM-0037 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 52
|  | 27 | 2506600-IESL-PID-P-0001 | P&ID - Inlet Gas Scrubber | IFH |  |  | 2025-08-01 | 2025-08-04 | PRMS-IESL-AGAS-TRN-0046 | B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 |  |  |  |  | 2025-08-22 | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 1 |  |  |  | 2025-09-26
|  | 28 | 2506600-IESL-PID-P-0002 | P&ID - SALES GAS Heater | IFH |  |  | 2025-08-01 | 2025-08-25 | PRMS-IESL-AGAS-TRN-0091 | B | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C2 |  |  |  |  | 2025-08-22 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0056 | 2025-09-15 | C2 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0182 | 1 |  |  |  | 2025-09-26
|  | 29 | 2506600-IESL-PID-P-0003 | P&ID - Pressure Regulating System | IFH |  |  | 2025-08-01 | 2025-08-06 | PRMS-IESL-AGAS-TRN-0051 | B | 2506600-AGAS-IESL-TRM-0025 | 2025-07-13 | C2 |  |  |  |  | 2025-08-22 | 2025-08-22 | PRMS-IESL-AGAS-TRN-0090 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C2 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0159 | 1 |  |  |  | 2025-09-26
|  | 30 | 2506600-IESL-PID-P-0004 | P&ID - Vent Header tie-in |  |  |  | 2025-08-01 | [10 empty] | 2025-08-22 | [17 empty] | 2025-09-26
|  | 31 | 2506600-IESL-PID-P-0005 | P&ID - Closed & Open Drain tie-in |  |  |  | 2025-08-01 | [10 empty] | 2025-08-22 | [17 empty] | 2025-09-26
|  | 32 | 2506600-IESL-PID-P-0006D | P&ID - Demo - SLOP VENT SCRUBBER AND VENT STACK AT UNICEM PRMS | AFC |  |  | 2025-07-11 | 2025-07-17 | PRMS-IESL-AGAS-TRN-0014 | B | 2506600-AGAS-IESL-TRM-0015 | 2025-07-21 | C1 |  |  |  |  | 2025-08-08 | [17 empty] | 2025-09-05 | 2025-08-15 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0073 | 1
|  | 33 | 2506600-IESL-PID-P-0007D | P&ID - Demo - Scraper Launcher at City Gate and AT UNICEM PRMS | AFC |  |  | 2025-07-11 | 2025-07-17 | PRMS-IESL-AGAS-TRN-0014 | B | 2506600-AGAS-IESL-TRM-0015 | 2025-07-21 | C1 |  |  |  |  | 2025-08-08 | [17 empty] | 2025-09-05 | 2025-08-15 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0073 | 1
|  | 34 | 2506600-IESL-BOD-P-0001 | Process & Flow Assurance Basis of Design | AFC |  |  | 2025-07-11 | 2025-07-16 | PRMS-IESL-AGAS-TRN-0010 | B | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 |  |  |  |  | 2025-08-08 | 2025-08-18 | PRMS-IESL-AGAS-TRN-0076 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 | [6 empty] | 2025-09-05 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0148 | 1
|  | 35 | 2506600-IESL-PID-P-0008D | P&ID - DEMO - PRESSURE REGULATING & METERING SKID AT UNICEM PRMS | AFC |  |  | 2025-07-11 | 2025-07-17 | PRMS-IESL-AGAS-TRN-0014 | B | 2506600-AGAS-IESL-TRM-0015 | 2025-07-21 | C1 |  |  |  |  | 2025-08-08 | [17 empty] | 2025-09-05 | 2025-08-15 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0073 | 1
|  | 36 | 2506600-IESL-UFD-P-0001 | UFD - Update (2 Nos) |  |  |  | 2025-07-18 | [10 empty] | 2025-08-15 | [17 empty] | 2025-09-12
|  | 37 | 2506600-IESL-RPT-P-0008 | Alarm and Trip Settings Report - Update | IFD |  |  | 2025-08-15 | 2025-09-03 | PRMS-IESL-AGAS-TRN-0123 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C2 |  |  |  |  | 2025-08-22 | 2025-09-15 | PRMS-IESL-AGAS-TRN-0171 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0071 | 2025-09-24 | C2 | [6 empty] | 2025-09-12
|  | 38 | 2506600-IESL-RPT-P-0009 | Liquid drop out mitigation strategy report | IFD |  |  | 2025-08-29 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0130 | B | 2506600-AGAS-IESL-TRM-0059 | 2025-09-17 | C2 | [5 empty] | 2025-10-03 | PRMS-IESL-AGAS-TRN-0237 | 0 | [14 empty] | 2025-09-12
Instrumentation
|  | 1 | 2506600-IESL-LST-J-0001 | Instrument I/O List | AFC |  |  | 2025-08-12 | 2025-09-02 | PRMS-IESL-AGAS-TRN-0117 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C1 |  |  |  |  | 2025-08-30 | [17 empty] | 2025-10-08 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0134 | 1 | 2506600-AGAS-IESL-TRM-0049 | 2025-09-09 | C1
|  | 2 | 2506600-IESL-LST-J-0002 | Instrument Index | IFD |  |  | 2025-08-06 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0057 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-08-25 | C2 |  |  |  |  | 2025-08-27 | 2025-09-24 | PRMS-IESL-AGAS-TRN-0209 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0077 | 2025-09-26 | C2 | [6 empty] | 2025-10-05
|  | 3 | 2506600-IESL-SHD-J-0001 | Instrument Cable Schedule |  |  |  | 2025-08-30 | [10 empty] | 2025-09-20 | [17 empty] | 2025-10-10
|  | 4 | 2506600-IESL-PHS-J-0001 | Instrumentation, Control and Automation Philosophy | AFC |  |  | 2025-08-05 | 2025-08-15 | PRMS-IESL-AGAS-TRN-0072 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-08-25 | C2 |  |  |  |  | 2025-08-25 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0165 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0054 | 2025-09-12 | C1 | [6 empty] | 2025-09-30 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0188 | 1 | 2506600-AGAS-IESL-TRM-0065 | 2025-09-19 | C1
|  | 5 | 2506600-IESL-SPC-J-0001 | General Instrument Specification | AFC |  |  | 2025-08-10 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0055 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-08-25 | C2 |  |  |  |  | 2025-08-30 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0160 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0053 | 2025-09-11 | C2 | [6 empty] | 2025-09-20 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0188 | 1 | 2506600-AGAS-IESL-TRM-0065 | 2025-09-19 | C1
|  | 6 | 2506600-IESL-DTS-J-0001 | Instrument Datasheet for Flow Instruments | IFR |  |  | 2025-08-20 | 2025-09-23 | PRMS-IESL-AGAS-TRN-0203 | B | 2506600-AGAS-IESL-TRM-0074 | 2025-09-25 | C2 |  |  |  |  | 2025-09-10 | [17 empty] | 2025-10-15 | [7 empty] | THIS SHOULD BE STAND ALONE FOR EACH INSTRUMENTATION
|  | 7 | 2506600-IESL-DTS-J-0002 | Instrument Datasheet for Level Gauge | AFC |  |  | 2025-08-20 | 2025-09-03 | 2506600-AGAS-IESL-TRM-0122 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C2 |  |  |  |  | 2025-09-10 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-10-15 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0197 | 1 | 2506600-AGAS-IESL-TRM-0069 | 2025-09-23 | C1
|  | 8 | 2506600-IESL-DTS-J-0003 | Instrument Datasheet for Pressure Gauge | AFC |  |  | 2025-08-20 | 2025-09-03 | 2506600-AGAS-IESL-TRM-0122 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C1 |  |  |  |  | 2025-09-10 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0134 | 0 | [14 empty] | 2025-10-15 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0134 | 1 | 2506600-AGAS-IESL-TRM-0049 / 0068 / 0057 0070 | 2025-09-09 | C1 / C2
|  | 9 | 2506600-IESL-DTS-J-0004 | Instrument Datasheet for Temperature Gauge | AFC |  |  | 2025-08-20 | 2025-09-03 | 2506600-AGAS-IESL-TRM-0122 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C2 |  |  |  |  | 2025-09-10 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-10-15 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0197 | 1 | 2506600-AGAS-IESL-TRM-0069 | 2025-09-23 | C1
|  | 10 | 2506600-IESL-DTS-J-0005 | Instrument Datasheet for On-Off Valve | AFC |  |  | 2025-08-20 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0166 | B | 2506600-AGAS-IESL-TRM-0054 | 2025-09-12 | C1 |  |  |  |  | 2025-09-10 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0188 | 0 | [14 empty] | 2025-10-15 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0188 | 1 | 2506600-AGAS-IESL-TRM-0065 / 0068 / 0070 | 2025-09-19 | C2
|  | 11 | 2506600-IESL-DTS-J-0006 | Instrument Datasheet for PSV | IFD |  |  | 2025-08-20 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0131 | B | 2506600-AGAS-IESL-TRM-0047 | 2025-09-08 | C2 |  |  |  |  | 2025-09-10 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0167 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0057 | 2025-09-15 | C2 | [6 empty] | 2025-10-15
|  | 12 | 2506600-IESL-DTS-J-0007 | Instrument Datasheet for Control Valve | IFD |  |  | 2025-08-20 | 2025-08-08 | PRMS-IESL-AGAS-TRN-0057 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-08-25 | C2 |  |  |  |  | 2025-09-10 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0167 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0057 | 2025-09-15 | C2 | [6 empty] | 2025-10-15
|  | 13 | 2506600-IESL-DTS-J-0008 | Instrument Datasheet for Pressure Switch | AFC |  |  | 2025-08-25 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0146 | B | 2506600-AGAS-IESL-TRM-0051 / 0068 | 2025-09-10 | C1 / C2 |  |  |  |  | 2025-09-15 | 2025-09-25 | PRMS-IESL-AGAS-TRN-0212 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0077 | 2025-09-26 | C2 | [6 empty] | 2025-10-15 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0225 | 1 | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C1
|  | 14 | 2506600-IESL-DTS-J-0009 | Instrument Datasheet for Level Switch | IFD |  |  | 2025-08-25 | 2025-09-23 | PRMS-IESL-AGAS-TRN-0203 | B | 2506600-AGAS-IESL-TRM-0073 / 0074 | 2025-09-25 | C2 |  |  |  |  | 2025-09-15 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0239 | 0 | [14 empty] | 2025-10-15
|  | 15 | 2506600-IESL-DTS-J-0010 | Instrument Datasheet for Pressure Controller | AFC |  |  | 2025-08-25 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0131 | B | 2506600-AGAS-IESL-TRM-0047 | 2025-09-08 | C1 |  |  |  |  | 2025-09-15 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0188 | 0 | [14 empty] | 2025-10-15 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0142 | 1 | 2506600-AGAS-IESL-TRM-0051 / 0057 / 0068 / 0070 | 2025-09-10 | C1 / C2 / C2
|  | 16 | 2506600-IESL-DTS-J-0011 | Instrument Datasheet for Level Controller | AFC |  |  | 2025-08-25 | 2025-09-12 | PRMS-IESL-AGAS-TRN-0166 | B | 2506600-AGAS-IESL-TRM-0054 | 2025-09-12 | C1 |  |  |  |  | 2025-09-15 | 2025-09-25 | PRMS-IESL-AGAS-TRN-0212 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0077 | 2025-09-26 | C2 | [6 empty] | 2025-10-15 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0225 | 1 | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2
|  | 17 | 2506600-IESL-DTS-J-0012 | Instrument Datasheet for Restriction Orifice
|  | 18 | 2506600-IESL-CAF-J-0001 | Instrument Cause & Effect Matrix | AFC |  |  | 2025-08-10 | 2025-09-02 | PRMS-IESL-AGAS-TRN-0117 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C2 |  |  |  |  | 2025-08-30 | 2025-09-24 | PRMS-IESL-AGAS-TRN-0207 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0077 | 2025-09-26 | C2 | [6 empty] | 2025-10-05 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0225 | 1 | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2
|  | 19 | 2506600-IESL-MTO-J-0001 | Instrument MTO (Priced and Unpriced) |  |  |  | 2025-10-05 | [10 empty] | 2025-10-15 | [17 empty] | 2025-10-23
|  | 20 | 2506600-IESL-LYT-J-0001 | Instrument Location Layout |  |  |  | 2025-08-28 | [10 empty] | 2025-09-25 | [17 empty] | 2025-10-15
|  | 21 | 2506600-IESL-LYT-J-0002 | Instrument Cable Tray Routing Layout |  |  |  | 2025-09-05 | [10 empty] | 2025-09-30 | [17 empty] | 2025-10-20
|  | 22 | 2506600-IESL-DRA-J-0001 | Instrument Hook-Up Drawing/Details |  |  |  | 2025-08-10 | [10 empty] | 2025-08-30 | [17 empty] | 2025-09-25
|  | 23 | 2506600-IESL-HUK-J-0001 | Instrument Hook-Up Drawing/Details for Level Gauge | AFC |  |  | 2025-08-10 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0063 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-07-25 | C2 |  |  |  |  | 2025-08-30 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-09-25 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0184 | 1 | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C1
|  | 24 | 2506600-IESL-HUK-J-0002 | Instrument Hook-Up Drawing/Details for Pressure Gauge | AFC |  |  | 2025-08-10 | 2025-08-21 | PRMS-IESL-AGAS-TRN-0087 | B | 2506600-AGAS-IESL-TRM-0044 | 2025-09-04 | C2 |  |  |  |  | 2025-08-30 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-09-25 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0184 | 1 | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C1
|  | 25 | 2506600-IESL-HUK-J-0003 | Instrument Hook-Up Drawing/Details for Temperature Gauge | AFC |  |  | 2025-08-10 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0063 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-07-25 | C2 |  |  |  |  | 2025-08-30 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0131 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0047 | 2025-09-08 | C2 | [6 empty] | 2025-09-25 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0142 | 1 | 2506600-AGAS-IESL-TRM-0051 / 0057 | 2025-09-10 | C1 / C2
|  | 26 | 2506600-IESL-HUK-J-0004 | Instrument Hookup Drawing/Details for On-Off Valve | AFC |  |  | 2025-08-10 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0063 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-07-25 | C2 |  |  |  |  | 2025-08-30 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-09-25 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0185 | 1 | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C1
|  | 27 | 2506600-IESL-HUK-J-0005 | Instrument Hook-Up Drawing/Details for level control valve | AFC |  |  | 2025-08-15 | 2025-08-21 | PRMS-IESL-AGAS-TRN-0087 | B | 2506600-AGAS-IESL-TRM-0039 | 2025-09-02 | C2 |  |  |  |  | 2025-09-05 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0145 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C1 | [6 empty] | 2025-09-25 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0184 | 1 | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C1
|  | 28 | 2506600-IESL-HUK-J-0006 | Instrument Hook-Up Drawing/Details for Pressure Control Valve | IFD |  |  | 2025-08-10 | 2025-08-21 | PRMS-IESL-AGAS-TRN-0087 | B | 2506600-AGAS-IESL-TRM-0039 | 2025-09-02 | C2 |  |  |  |  | 2025-08-30 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0239 | 0 | [14 empty] | 2025-09-25
|  | 29 | 2506600-IESL-HUK-J-0007 | Instrument Hook-Up Drawing/Details for Pressure Switch | AFC |  |  | 2025-08-15 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0099 | B | 2506600-AGAS-IESL-TRM-0039 | 2025-09-02 | C1 |  |  |  |  | 2025-09-05 | [17 empty] | 2025-09-25 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0131 | 1 | 2506600-AGAS-IESL-TRM-0047 / 0057 | 2025-09-08 | C1 / C2
|  | 30 | 2506600-IESL-HUK-J-0008 | Instrument Hook-Up Drawing/Details for Level Switch | AFC |  |  | 2025-08-15 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0099 | B | 2506600-AGAS-IESL-TRM-0039 | 2025-09-02 | C1 |  |  |  |  | 2025-09-05 | [17 empty] | 2025-09-25 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0131 | 1 | 2506600-AGAS-IESL-TRM-0047 / 0057 | 2025-09-08 | C1 / C2
|  | 31 | 2506600-IESL-DRA-J-0002 | Instrument Loop Drawing |  |  |  | 2025-09-10 | [10 empty] | 2025-09-30 | [17 empty] | 2025-10-20
|  | 32 | 2506600-IESL-DGM-J-0001 | Instrument Junction Box Wiring Diagram |  |  |  | 2025-08-25 | [10 empty] | 2025-09-20 | [17 empty] | 2025-10-10
|  | 33 | 2506600-IESL-DGM-J-0002 | Control System Architectural Diagram (Update) |  |  |  | 2025-08-30 | [10 empty] | 2025-09-10 | [17 empty] | 2025-10-05
|  | 34 | 2506600-IESL-CAL-J-0001 | Preliminary Sizing Calculation (Actuator) |  |  |  | 2025-08-25 | [10 empty] | 2025-09-20 | [17 empty] | 2025-10-15
|  | 35 | 2506600-IESL-BOD-J-0001 | Instrument Basis of Design | IFD |  |  | 2025-07-24 | 2025-07-28 | PRMS-IESL-AGAS-TRN-0032 | B | 2506600-AGAS-IESL-TRM-0034 | 2025-07-25 | C2 |  |  |  |  | 2025-08-21 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0213 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0079 | 2025-09-30 | C1 | [6 empty] | 2025-09-18
Piping
|  | 1 | 2506600-IESL-SPC-L-0001 | Piping Material Specification | AFC |  | 2025-07-31 | 2025-07-31 | 2025-08-19 | PRMS-IESL-AGAS-TRN-0080 | B | 2506600-AGAS-IESL-TRM-0033 | 2025-08-25 | C2 |  |  |  |  | 2025-08-26 | 2025-08-28 | PRMS-IESL-AGAS-TRN-0104 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0041 | 2025-09-03 | C2 | [6 empty] | 2025-09-16 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0181 | 1 | 2506600-AGAS-IESL-TRM-0063 | 2025-09-18 | C2
|  | 2 | 2506600-IESL-BOD-L-0001 | Piping Design Basis | AFC |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | PRMS-IESL-AGAS-TRN-0034 | B | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 |  |  |  |  | 2025-08-22 | 2025-08-20 | PRMS-IESL-AGAS-TRN-0082 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0030 | 2025-08-20 | C2 | [6 empty] | 2025-09-12 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0096 | 1 | 2506600-AGAS-IESL-TRM-0036 | 2025-08-26 | C1
|  | 3 | 2506600-IESL-SPC-L-0002 | Specification for Stress Analysis | IFD |  | 2025-08-18 | 2025-08-18 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0157 | B | 2506600-AGAS-IESL-TRM-0058 | 2025-09-15 | C2 |  |  |  |  | 2025-09-03 | 2025-08-30 | PRMS-IESL-AGAS-TRN-0224 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0083 | 2025-10-06 | C2 | [6 empty] | 2025-09-23
|  | 4 | 2506600-IESL-SPC-L-0003 | Standard Pipe Support Specification | IFR |  | 2025-08-15 | 2025-08-15 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0246 | B | [7 empty] | 2025-08-29 | [17 empty] | 2025-09-20
|  | 5 | 2506600-IESL-TIL-L-0001 | Piping Tie-in List | AFC |  | 2025-08-18 | 2025-08-18 | 2025-08-20 | PRMS-IESL-AGAS-TRN-0084 | B | 2506600-AGAS-IESL-TRM-0030 | 2025-08-20 | C2 |  |  |  |  | 2025-08-29 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0101 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0041 | 2025-09-03 | C2 | [6 empty] | 2025-09-28 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0241 | 1
|  | 6 | 2506600-IESL-LST-L-0001 | Manual Valve List | AFC |  | 2025-08-08 | 2025-08-08 | 2025-08-21 | PRMS-IESL-AGAS-TRN-0088 | B | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 |  |  |  |  | 2025-08-28 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0183 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0063 | 2025-09-18 | C2 | [6 empty] | 2025-09-28 | 2025-09-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0219 | 1
|  | 7 | 2506600-IESL-DTS-L-0001 | Manual Valve Datasheets | IFD |  | 2025-08-20 | 2025-08-20 | 2025-09-11 | PRMS-IESL-AGAS-TRN-0164 | B | 2506600-AGAS-IESL-TRM-0061 | 2025-09-17 | C2 |  |  |  |  | 2025-09-12 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0230 | 0 | [14 empty] | 2025-10-03
|  | 8 | 2506600-IESL-LST-L-0002 | Critical Line List | IFD |  | 2025-08-15 | 2025-08-15 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0132 | B | 2506600-AGAS-IESL-TRM-0058 | 2025-09-15 | C2 |  |  |  |  | 2025-09-07 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0198 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0076 | 2025-09-25 | C2 | [6 empty] | 2025-09-27
|  | 9 | 2506600-IESL-RPT-L-0001 | Piping Stress Analysis Report |  |  | 2025-09-09 | 2025-09-09 | [10 empty] | 2025-10-10 | [17 empty] | 2025-10-18
|  | 10 | 2506600-IESL-LST-L-0003 | Piping Specialty Item List | AFC |  | 2025-08-18 | 2025-08-18 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0153 | B | 2506600-AGAS-IESL-TRM-0051 | 2025-09-10 | C2 |  |  |  |  | 2025-09-09 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0183 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0063 | 2025-09-18 | C2 | [6 empty] | 2025-09-30 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0227 | 1 | 2506600-AGAS-IESL-TRM-0082 | 2025-10-02 | C1
|  | 11 | 2506600-IESL-DTS-L-0002 | Specialty Items Datasheets | AFC |  | 2025-08-25 | 2025-08-25 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0132 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C2 |  |  |  |  | 2025-09-18 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0191 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0067 | 2025-09-19 | C2 | [6 empty] | 2025-10-07 | 2025-09-25 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0211 | 1 | 2506600-AGAS-IESL-TRM-0076 | 2025-09-25 | C1
|  | 12 | 2506600-IESL-MTO-L-0001 | Piping Bulk MTO |  |  | 2025-09-19 | 2025-09-19 | [10 empty] | 2025-09-26 | [17 empty] | 2025-10-20
|  | 13 | 2506600-IESL-RPT-L-0002 | Layout Review Report |  |  | 2025-09-05 | 2025-09-05 | [10 empty] | 2025-09-25 | [17 empty] | 2025-10-14
|  | 14 | 2506600-IESL-PLN-L-0002 | Equipment Location Plan | IFD |  | 2025-08-05 | 2025-08-05 | 2025-08-14 | PRMS-IESL-AGAS-TRN-0070 | B | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 |  |  |  |  | 2025-08-24 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0242 | 0 | [14 empty] | 2025-09-13
|  | 15 | 2506600-IESL-DRA-L-0001D | Piping Demolition Drawing | AFC |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | PRMS-IESL-AGAS-TRN-0043 | B | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 |  |  |  |  | 2025-08-20 | 2025-08-19 | PRMS-IESL-AGAS-TRN-0081 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 | [6 empty] | 2025-09-12 | 2025-09-03 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0125 | 1 | 2506600-AGAS-IESL-TRM-0046 | 2025-09-08 | C1
|  | 16 | 2506600-IESL-PLN-L-0001 | Overall Key Plan for Piping General Arrangment | IFR |  | 2025-08-20 | 2025-08-20 | 2025-09-15 | PRMS-IESL-AGAS-TRN-0170 | B | 2506600-AGAS-IESL-TRM-0061 | 2025-09-17 | C2 |  |  |  |  | 2025-09-15 | [17 empty] | 2025-10-02
|  | 17 | 2506600-IESL-DRA-L-0001 | Piping General Arrangment Drawing-Inlet Gas Scrubber Area | IFR |  | 2025-08-20 | 2025-08-20 | 2025-09-16 | PRMS-IESL-AGAS-TRN-0174 | B | 2506600-AGAS-IESL-TRM-0060 | 2025-09-17 | C2 |  |  |  |  | 2025-09-15 | [17 empty] | 2025-10-02
|  | 18 | 2506600-IESL-DRA-L-0002 | Piping General Arrangment Drawing-Heater Area | IFR |  | 2025-08-20 | 2025-08-20 | 2025-09-16 | PRMS-IESL-AGAS-TRN-0174 | B | 2506600-AGAS-IESL-TRM-0060 | 2025-09-17 | C2 |  |  |  |  | 2025-09-15 | [17 empty] | 2025-10-04
|  | 19 | 2506600-IESL-DRA-L-0003 | Piping General Arrangment Drawing-PRMS-(PCV-SDV) Area | IFR |  | 2025-08-20 | 2025-08-20 | 2025-09-16 | PRMS-IESL-AGAS-TRN-0174 | B | 2506600-AGAS-IESL-TRM-0060 | 2025-09-17 | C2 |  |  |  |  | 2025-09-15 | [17 empty] | 2025-10-04
|  | 20 | 2506600-IESL-ISO-L-0001 | Piping Isometric Drawings |  |  | 2025-09-16 | 2025-09-16 | [10 empty] | 2025-09-26 | [17 empty] | 2025-10-15
|  | 21 | 2506600-IESL-SHD-L-0001 | Pipe Support Schedule |  |  | 2025-08-22 | 2025-08-22 | [10 empty] | 2025-09-05 | [17 empty] | 2025-10-15
|  | 22 | f | Technical Design Review Report
|  | 23 | 2506600-IESL-RPT-L-0004 | 90% Technical Design Review
Mechanical
|  | 1 | 2506600-IESL-SPC-M-0001 | Specifications for All New Equipment | AFC |  | 2025-07-02 | 2025-07-09 | 2025-07-09 | PRMS-IESL-AGAS-TRN-0006 | B | 2506600-AGAS-IESL-TRM-0013 | 2025-07-18 | C2 |  |  |  |  | 2025-07-30 | 2025-07-22 | PRMS-IESL-AGAS-TRN-0022 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 | [6 empty] | 2025-08-20 | 2025-08-05 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0047 | 1 | 2506600-AGAS-IESL-TRM-0024 | 2025-08-07 | C2
|  | 2 | 2506600-IESL-CAL-M-0001 | Sizing Calculation for Inlet Gas Scrubber | AFC |  | 2025-08-08 | 2025-08-15 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0064 | B | 2506600-AGAS-IESL-TRM-0028 | 2025-08-20 | C2 |  |  |  |  | 2025-08-29 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0136 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C1 | [6 empty] | 2025-09-19 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0240 | 1
|  | 3 | 2506600-IESL-DTS-M-0001 | Data Sheet for Inlet Gas Scrubber | AFC |  | 2025-08-15 | 2025-08-22 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0064 | B | 2506600-AGAS-IESL-TRM-0028 / 0041 | 2025-08-20 | C2 |  |  |  |  | 2025-09-05 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0136 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C2 | [6 empty] | 2025-09-19 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0240 | 1
|  | 4 | 2506600-IESL-DTS-M-0002 | Data sheet for Sales Gas Heater | IFD |  | 2025-08-18 | 2025-08-25 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0137 | B | 2506600-AGAS-IESL-TRM-0050 | 2025-09-09 | C2 |  |  |  |  | 2025-09-08 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0178 | 0 | [14 empty] | 2025-09-22
|  | 5 | 2506600-IESL-RFQ-M-0001 | Request for Quotation for Inlet Gas Scrubber | IFD |  | 2025-08-22 | 2025-08-29 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0141 | B | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C2 |  |  |  |  | 2025-09-12 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0194 | 0 | [14 empty] | 2025-09-26
|  | 6 | 2506600-IESL-RFQ-M-0002 | Request for Quotation for Sales Gas Heater | IFD |  | 2025-08-25 | 2025-09-01 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0179 | B | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C2 |  |  |  |  | 2025-09-15 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0232 | 0 | [14 empty] | 2025-09-29
|  | 7 | 2506600-IESL-DRA-M-0004 | General Arrangement Drawing for Inlet Gas Scrubber | AFC |  | 2025-08-22 | 2025-08-29 | 2025-08-14 | PRMS-IESL-AGAS-TRN-0069 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-09-12 | 2025-08-15 | PRMS-IESL-AGAS-TRN-0074 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0033 | 2025-07-25 | C2 | [6 empty] | 2025-09-26 | 2025-08-29 | PRMS-IESL-AGAS-TRN-0022 | PRMS-IESL-AGAS-TRN-0110 / 0135 / 0240 | 1 / 2 | 2506600-AGAS-IESL-TRM-0040 / 0052 | 2025-09-02 | C2 / C1
|  | 8 | 2506600-IESL-DRA-M-0005 | General Arrangement Drawing for Sales Gas Heater | IFD |  | 2025-08-25 | 2025-09-01 | 2025-09-08 | PRMS-IESL-AGAS-TRN-0137 | B | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C2 |  |  |  |  | 2025-09-15 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0194 | 0 | [14 empty] | 2025-09-29
|  | 9 | 2506600-IESL-LST-M-0001 | Long Lead Items (Mechanical, Piping & Instrumentation) | IFD |  | 2025-07-09 | 2025-07-16 | 2025-07-21 | PRMS-IESL-AGAS-TRN-0017 | B | 2506600-AGAS-IESL-TRM-0017 | 2025-07-23 | C2 |  |  |  |  | 2025-08-06 | 2025-09-01 | PRMS-IESL-AGAS-TRN-0168 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0058 | 2025-09-15 | C2 | [6 empty] | 2025-08-27
|  | 10 | 2506600-IESL-TBE-M-0001 | Technical Bid Evaluation (TBE) for Inlet Gas Scrubber | IFD |  | 2025-08-29 | 2025-09-05 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0141 | B | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C2 |  |  |  |  | 2025-09-19 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0194 | 0 | [14 empty] | 2025-10-03
|  | 11 | 2506600-IESL-TBE-M-0002 | Technical Bid Evaluation for Sales Gas Heater | IFD |  | 2025-09-01 | 2025-09-08 | 2025-09-18 | PRMS-IESL-AGAS-TRN-0179 | B | 2506600-AGAS-IESL-TRM-0064 | 2025-09-19 | C2 |  |  |  |  | 2025-09-22 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0232 | 0 | [14 empty] | 2025-10-06
|  | 12 | 2506600-IESL-PHS-L-0001 | Materials Handling Philosophy | IFR |  |  | 2025-09-10 | 2025-09-24 | PRMS-IESL-AGAS-TRN-0208 | B | 2506600-AGAS-IESL-TRM-0078 | 2025-09-26 | C2 |  |  |  |  | 2025-09-24 | [17 empty] | 2025-10-08
Civil/Structural
|  | 1 | 2506600-IESL-BOD-C-0002 | Civil-Structural Basis of Design | IFD |  |  | 2025-07-25 | 2025-07-29 | PRMS-IESL-AGAS-TRN-0035 | B | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 |  |  |  |  | 2025-08-08 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0126 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 | [6 empty] | 2025-09-26
|  | 2 | 2506600-IESL-SPC-C-0001 | Specification of Steel Works | IFD |  |  | 2025-08-01 | 2025-07-29 | PRMS-IESL-AGAS-TRN-0035 | B | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 |  |  |  |  | 2025-08-12 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0126 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 | [6 empty] | 2025-09-30
|  | 3 | 2506600-IESL-SPC-C-0002 | Specification for Foundation | IFD |  |  | 2025-08-08 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0065 | B | 2506600-AGAS-IESL-TRM-0027 | 2025-08-18 | C2 |  |  |  |  | 2025-08-15 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0126 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 | [6 empty] | 2025-09-19
|  | 4 | 2506600-IESL-SPC-C-0003 | Specification for Concrete Works | IFD |  |  | 2025-08-15 | 2025-08-13 | PRMS-IESL-AGAS-TRN-0065 | B | 2506600-AGAS-IESL-TRM-0031 | 2025-08-21 | C2 |  |  |  |  | 2025-08-22 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0126 | 0 | [14 empty] | 2025-09-19
|  | 5 | 2506600-IESL-RPT-C-0001 | Equipment Foundation Design Report | IFR |  |  | 2025-09-10 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0234 | B | [7 empty] | 2025-09-17 | [17 empty] | 2025-09-26
|  | 6 | 2506600-IESL-SPC-C-0004 | Specification for Site Preparation and Earthworks | IFR |  |  | 2025-08-25 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0127 | B | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 |  |  |  |  | 2025-08-08 | [17 empty] | 2025-09-26
|  | 7 | 2506600-IESL-RPT-C-0002 | Pipe Support and Foundation Design Report |  |  |  | 2025-09-16 | [10 empty] | 2025-09-26 | [17 empty] | 2025-10-17
|  | 8 | 2506600-IESL-RPT-C-0003 | Drainage Design Calculation Report | IFR |  |  | 2025-09-07 | 2025-10-02 | PRMS-IESL-AGAS-TRN-0234 | B | [7 empty] | 2025-09-18 | [17 empty] | 2025-10-12
|  | 9 | 2506600-IESL-RPT-C-0004 | Pavement Design Calculation Report | IFR |  |  | 2025-08-20 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0127 | B | [7 empty] | 2025-09-18 | [17 empty] | 2025-10-12
|  | 10 | 2506600-IESL-MTO-C-0001 | Civil Structural MTO |  |  |  | 2025-09-25 | [10 empty] | 2025-09-25 | [17 empty] | 2025-10-12
|  | 11 | 2506600-IESL-LYT-C-0002 | Civil Site/Foundation Layout | IFR |  |  | 2025-09-08 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0189 | B | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 |  |  |  |  | 2025-09-15 | [17 empty] | 2025-10-10
|  | 12 | 2506600-IESL-LYT-C-0003 | Drainage Layout and Details | IFR |  |  | 2025-09-15 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0235 | B | [7 empty] | 2025-09-26 | [17 empty] | 2025-10-12
|  | 13 | 2506600-IESL-LYT-C-0004 | Pavement Layout and Details | IFR |  |  | 2025-08-27 | 2025-09-04 | PRMS-IESL-AGAS-TRN-0129 | B | 2506600-AGAS-IESL-TRM-0072 | 2025-09-24 | C2 |  |  |  |  | 2025-09-18 | [17 empty] | 2025-10-12
|  | 14 | 2506600-IESL-DET-C-0001 | Scrubber Foundation Plan, Sections and Details | IFR |  |  | 2025-09-13 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0235 | B | [7 empty] | 2025-09-12 | [17 empty] | 2025-09-26
|  | 15 | 2506600-IESL-DET-C-0002 | Heater Foundation Plan, Sections and Details | IFR |  |  | 2025-09-17 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0235 | B | [7 empty] | 2025-09-12 | [17 empty] | 2025-09-26
|  | 16 | 2506600-IESL-LYT-C-0001 | Pipe Support Details & Foundation |  |  |  | 2025-09-22 | [10 empty] | 2025-09-29 | [17 empty] | 2025-10-17
Electrical
|  | 1 | 2506600-IESL-PHS-E-0001 | Electrical Design Philosophy | AFC |  |  | 2025-08-04 | 2025-07-30 | PRMS-IESL-AGAS-TRN-0036 | B | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 |  |  |  |  | 2025-08-22 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0095 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0038 | 2025-09-01 | C2 | [6 empty] | 2025-09-08 | 2025-09-17 |  | PRMS-IESL-AGAS-TRN-0177 / 0200 / 0204 | 1 / 2 / 3 | 2506600-AGAS-IESL-TRM-0066 / 0069 / 0075 | 2025-09-19 | C2
|  | 2 | 2506600-IESL-PHS-E-0002 | Lightning Protection, Earthing and Bonding Philosophy |  |  |  | 2025-08-11 | [10 empty] | 2025-08-26 | [17 empty] | 2025-09-12
|  | 3 | 2506600-IESL-PHS-E-0003 | Lighting Philosophy |  |  |  | 2025-08-15 | [10 empty] | 2025-08-29 | [17 empty] | 2025-09-17
|  | 4 | 2506600-IESL-SPC-E-0001 | Cable Specification | AFC |  |  | 2025-08-18 | 2025-07-21 | PRMS-IESL-AGAS-TRN-0020 | B | 2506600-AGAS-IESL-TRM-0016 | 2025-07-23 | C2 |  |  |  |  | 2025-08-29 | 2025-08-01 | PRMS-IESL-AGAS-TRN-0045 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0023 | 2025-08-06 | C2 | [6 empty] | 2025-09-19 | 2025-08-19 |  | PRMS-IESL-AGAS-TRN-0078 | 1 | 2506600-AGAS-IESL-TRM-0030 | 2025-08-20 | C1
|  | 5 | 2506600-IESL-DTS-E-0001 | Datasheet for Cables | AFC |  |  | 2025-08-22 | 2025-08-11 | PRMS-IESL-AGAS-TRN-0061 | B | 2506600-AGAS-IESL-TRM-0025 | 2025-08-13 | C2 |  |  |  |  | 2025-09-05 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0095 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0038 | 2025-09-01 | C2 | [6 empty] | 2025-09-19 | 2025-09-16 |  | PRMS-IESL-AGAS-TRN-0175 / 0200 / 0204 | 1 / 2 / 3 | 2506600-AGAS-IESL-TRM-0066 / 0069 / 0075 | 2025-09-19 | C2
|  | 6 | 2506600-IESL-CAL-E-0001 | Illumination Calculation | IFD |  |  | 2025-08-29 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0193 | B | 2506600-AGAS-IESL-TRM-0068 | 2025-09-22 | C2 |  |  |  |  | 2025-09-15 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0243 | 0 | [14 empty] | 2025-09-26
|  | 7 | 2506600-IESL-CAL-E-0002 | Cable Sizing Calculation | IFR |  |  | 2025-09-01 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0221 | B | 2506600-AGAS-IESL-TRM-0081 | 2025-10-02 | C2 |  |  |  |  | 2025-09-12 | [17 empty] | 2025-09-26
|  | 8 | 2506600-IESL-MTO-E-0001 | Electrical MTO |  |  |  | 2025-09-22 | [10 empty] | 2025-10-06 | [17 empty] | 2025-10-17
|  | 9 | 2506600-IESL-LYT-E-0001 | Cable Routing Layout | IFR |  |  | 2025-09-12 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0245 | B | [7 empty] | 2025-09-26 | [17 empty] | 2025-10-10
2506600-IESL-TIL-L-0001 |  | 10 | 2506600-IESL-LYT-E-0002 | Cable Tray Layout |  |  |  | 2025-09-12 | [10 empty] | 2025-09-26 | [17 empty] | 2025-10-10
|  | 11 | 2506600-IESL-LYT-E-0003 | Lighting Layout Drawing | IFR |  |  | 2025-09-19 | 2025-09-19 | PRMS-IESL-AGAS-TRN-0187 | B | 2506600-AGAS-IESL-TRM-0067 | 2025-09-19 | C2 |  |  |  |  | 2025-10-03 | [17 empty] | 2025-10-17
|  | 12 | 2506600-IESL-LYT-E-0004 | Earthing Layout | IFR |  |  | 2025-09-24 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0245 | B | [7 empty] | 2025-10-08 | [17 empty] | 2025-10-22
|  | 13 | 2506600-IESL-SLD-E-0001 | Single Line Diagram (Update) | IFR |  |  | 2025-09-30 | 2025-09-30 | PRMS-IESL-AGAS-TRN-0226 | B | 2506600-AGAS-IESL-TRM-0080 | 2025-10-02 | C2 |  |  |  |  | 2025-10-14 | [17 empty] | 2025-10-22
|  | 14 | 2506600-IESL-LST-E-0001 | Electrical Load list | IFD |  |  | 2025-09-12 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0102 | B | 2506600-AGAS-IESL-TRM-0038 | 2025-09-01 | C2 |  |  |  |  | 2025-09-26 | 2025-09-24 | PRMS-IESL-AGAS-TRN-0206 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0079 | 2025-09-30 | C2 | [6 empty] | 2025-10-10
|  | 15 | 2506600-IESL-SPC-E-0002 | Electrical Bulk Equipment Specification | AFC |  |  | 2025-08-11 | 2025-07-31 | PRMS-IESL-AGAS-TRN-0040 | B | 2506600-AGAS-IESL-TRM-0025 | 2025-08-13 | C2 |  |  |  |  | 2025-08-26 | 2025-08-27 | PRMS-IESL-AGAS-TRN-0095 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0038 | 2025-09-01 | C2 | [6 empty] | 2025-10-10 | 2025-09-17 |  | PRMS-IESL-AGAS-TRN-0176 | 1 | 2506600-AGAS-IESL-TRM-0066 | 2025-09-19 | C1
|  | 16 | 2506600-IESL-DET-E-0001 | Electrical Typical Installation details | IFD |  |  | 2025-09-08 | 2025-09-09 | PRMS-IESL-AGAS-TRN-0139 | B | 2506600-AGAS-IESL-TRM-0053 | 2025-09-11 | C2 |  |  |  |  | 2025-09-19 | 2025-10-03 | PRMS-IESL-AGAS-TRN-0236 | 0 | [14 empty] | 2025-09-30
|  | 17 | 2506600-IESL-SCH-E-0001 | Distribution board schematics |  |  |  | 2025-09-15 | [10 empty] | 2025-09-26 | [17 empty] | 2025-10-06
Corrosion
|  | 1 | 2506600-IESL-RPT-Z-0001 | Material Selection Report |  |  |  | 2025-08-29 | [10 empty] | 2025-09-12 | [17 empty] | 2025-10-03
|  | 2 | 2506600-IESL-DGM-Z-0001 | Material Selection Diagram |  |  |  | 2025-08-29 | [10 empty] | 2025-09-12 | [17 empty] | 2025-10-03
|  | 3 | 2506600-IESL-SPC-Z-0001 | Painting Specification : Piping, Vessels, Steel Structures & Equipment | AFC |  |  | 2025-07-18 | 2025-07-18 | PRMS-IESL-AGAS-TRN-0016 | B | 2506600-AGAS-IESL-TRM-0015 | 2025-07-21 | C2 |  |  |  |  | 2025-08-15 | 2025-08-06 | PRMS-IESL-AGAS-TRN-0050 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0024 | 2025-08-07 | C1 | [6 empty] | 2025-09-26 | 2025-08-11 |  | PRMS-IESL-AGAS-TRN-0059 | 1 | 2506600-AGAS-IESL-TRM-0025 | 2025-08-13 | C1
|  | 4 | 2506600-IESL-SPC-Z-0002 | Welding specification | AFC |  |  | 2025-07-25 | 2025-07-25 | PRMS-IESL-AGAS-TRN-0029 | B | 2506600-AGAS-IESL-TRM-0021 | 2025-07-29 | C2 |  |  |  |  | 2025-08-15 | 2025-08-06 | PRMS-IESL-AGAS-TRN-0049 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0025 | 2025-08-13 | C2 | [6 empty] | 2025-09-26 | 2025-08-25 |  | PRMS-IESL-AGAS-TRN-0093 | 1 | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C1
|  | 5 | 2506600-IESL-SPC-Z-0003 | NDE Specification | AFC |  |  | 2025-08-01 | 2025-08-11 | PRMS-IESL-AGAS-TRN-0060 | B | 2506600-AGAS-IESL-TRM-0030 | 2025-08-20 | C2 |  |  |  |  | 2025-09-05 | 2025-08-25 | PRMS-IESL-AGAS-TRN-0092 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0035 | 2025-08-26 | C2 | [6 empty] | 2025-09-26 | 2025-09-01 |  | PRMS-IESL-AGAS-TRN-0114 | 1 | 2506600-AGAS-IESL-TRM-0042 | 2025-09-04 | C1
|  | 6 | 2506600-IESL-SPC-Z-0004 | Specification for Insulating Flange and Kits | AFC |  |  | 2025-08-01 | 2025-08-12 | PRMS-IESL-AGAS-TRN-0062 | B | 2506600-AGAS-IESL-TRM-0026 | 2025-08-14 | C2 |  |  |  |  | 2025-09-05 | 2025-08-25 | PRMS-IESL-AGAS-TRN-0092 | 0 | [5 empty] | 2506600-AGAS-IESL-TRM-0041 | 2025-09-03 | C1 | [6 empty] | 2025-09-26 | 2025-09-10 |  | PRMS-IESL-AGAS-TRN-0143 | 1 | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C1
|  | 7 | 2506600-IESL-SPC-Z-0005 | Specification for Insulation and Cladding. | IFR |  |  | 2025-09-05 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0247 | B | [7 empty] | 2025-09-20 | [17 empty] | 2025-10-05
|  | 8 | 2506600-IESL-MTO-Z-0001 | Insulation and Cladding MTO |  |  |  | 2025-10-02 | [10 empty] | 2025-10-12 | [17 empty] | 2025-10-19
|  | 9 | 2506600-IESL-SPC-Q-0001 | Hydrotest Specification | IFR |  |  | 2025-09-05 | 2025-09-10 | PRMS-IESL-AGAS-TRN-0143 | B | 2506600-AGAS-IESL-TRM-0052 | 2025-09-11 | C2 |  |  |  |  | 2025-09-20 | 2025-10-06 | PRMS-IESL-AGAS-TRN-0248 | 0 | [14 empty] | 2025-10-05
Formulas:
AFC = [IFD]+10
Note on J72: Okafor Chinelo: 2506600-IESL-PID-P-0007D P&ID - DEMO - PRESSURE REGULATING & METERING SKID AT UNICEM PRMS STATION was swapped with 2506600-IESL-PID-P-0008D P&ID - Demo - Scraper Launcher at City Gate and AT UNICEM PRMS STATION
Note on J74: Okafor Chinelo: 2506600-IESL-PID-P-0008D P&ID - Demo - Scraper Launcher at City Gate and AT UNICEM PRMS STATION was swapped with 2506600-IESL-PID-P-0007D P&ID - DEMO - PRESSURE REGULATING & METERING SKID AT UNICEM PRMS STATION
Note on Y132: M. Ayanwande: This date is too late for input into Pipe Support for Civil to issue IFD by the end of August
Note on Y133: M. Ayanwande: This date is too late for input into Pipe Support for Civil to issue IFD by the end of August
Note on Y134: M. Ayanwande: This date is too late for input into Pipe Support for Civil to issue IFD by the end of August
Note on Y135: M. Ayanwande: This date is too late for input into Pipe Support for Civil to issue IFD by the end of August

## ISOs
Technical safety abbreviation
[7 empty] | IFR | [7 empty] | IFD | [8 empty] | AFC |  |  |  |  | REMARKS
CONTRATOR's Doc No |  |  | Piping Isometric Drawings |  |  | START | Rev B |  |  |  | TR NO | Date Sent | Rev Sta | Issue For | Rev 0 |  |  |  | TR No | Date Sent | Rev Sta | Issue For | Next Rev | Rev 1 |  | TR No
| S/No | DOC Number | DOC Title | Status | Definition |  | Planned | Actual | Transmittal | Rev |  |  |  |  | Planned | Actual | Transmittal | Rev | [5 empty] | Planned | Actual |  | Transmittal | Rev
Piping
| 1 | 2506600-IESL-ISO-L-0001-01 | Piping Isometric Drawings_10"-PG-B1-1001 |  |  | 2025-09-16 | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 2 | 2506600-IESL-ISO-L-0002-01 | Piping Isometric Drawings_10"-PG-B1-1002 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 3 | 2506600-IESL-ISO-L-0003-01 | Piping Isometric Drawings_8"-PG-B1-1018 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 4 | 2506600-IESL-ISO-L-0004-01 | Piping Isometric Drawings_8"-PG-B1-1019 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 5 | 2506600-IESL-ISO-L-0005-01 | Piping Isometric Drawings_8"-PG-B1-1020 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 6 | 2506600-IESL-ISO-L-0006-01 | Piping Isometric Drawings_8"-PG-B1-1040 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 7 | 2506600-IESL-ISO-L-0007-01 | Piping Isometric Drawings_8"-PG-B1-1017 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 8 | 2506600-IESL-ISO-L-0008-01 | Piping Isometric Drawings_12"-PG-B1-1021 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 9 | 2506600-IESL-ISO-L-0009-01 | Piping Isometric Drawings_12"-PG-B1-1010 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 10 | 2506600-IESL-ISO-L-0010-01 | Piping Isometric Drawings_10"-PG-B1-1033 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 11 | 2506600-IESL-ISO-L-0011-01 | Piping Isometric Drawings_10"-PG-B1-1011 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 12 | 2506600-IESL-ISO-L-0012-01 | Piping Isometric Drawings_10"-PG-B1-1013 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 13 | 2506600-IESL-ISO-L-0013-01 | Piping Isometric Drawings_10"-PG-B1-1015 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 14 | 2506600-IESL-ISO-L-0014-01 | Piping Isometric Drawings_16"-PG-A1-1012 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 15 | 2506600-IESL-ISO-L-0015-01 | Piping Isometric Drawings_16"-PG-A1-1014 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 16 | 2506600-IESL-ISO-L-0016-01 | Piping Isometric Drawings_16"-PG-A1-1016 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 17 | 2506600-IESL-ISO-L-0017-01 | Piping Isometric Drawings_18"-PG-A1-1017 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 18 | 2506600-IESL-ISO-L-0018-01 | Piping Isometric Drawings_2"-PL-B1-1003 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 19 | 2506600-IESL-ISO-L-0019-01 | Piping Isometric Drawings_2"-PL-A1-1005 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 20 | 2506600-IESL-ISO-L-0020-01 | Piping Isometric Drawings_2"-PG-B1-1003 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 21 | 2506600-IESL-ISO-L-0021-01 | Piping Isometric Drawings_6"-V-A1-1009 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 22 | 2506600-IESL-ISO-L-0022-01 | Piping Isometric Drawings_2"-PG-B1-1030 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 23 | 2506600-IESL-ISO-L-0023-01 | Piping Isometric Drawings_3"-V-A1-1031 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 24 | 2506600-IESL-ISO-L-0024-01 | Piping Isometric Drawings_2"-FG-A1-1023 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 25 | 2506600-IESL-ISO-L-0025-01 | Piping Isometric Drawings_2"-V-A1-1022 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 26 | 2506600-IESL-ISO-L-0026-01 | Piping Isometric Drawings_2"-V-A2-1035 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 27 | 2506600-IESL-ISO-L-0027-01 | Piping Isometric Drawings_2"-PL-B1-1006 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 28 | 2506600-IESL-ISO-L-0028-01 | Piping Isometric Drawings_2"-PL-A1-1007 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 29 | 2506600-IESL-ISO-L-0029-01 | Piping Isometric Drawings_2"-FG-B1-1008 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 30 | 2506600-IESL-ISO-L-0030-01 | Piping Isometric Drawings_2"-FG-A1-1036 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15
| 31 | 2506600-IESL-ISO-L-0031-01 | Piping Isometric Drawings_2"-WP-A1-1034 |  |  |  | 2025-09-16 | [7 empty] | 2025-09-26 | [8 empty] | 2025-10-15